## Close Checklist
FMS — September 2026 Month-End Closing Checklist (8-day close, Foundation and Cambria)
Step | Day | Date | Activity | Category | What Done Looks Like (sub-steps and evidence) | System / Source | Responsible Party | Foundation (Y / N/A) | Cambria (Y / N/A) | Completed By / Date | Notes / Open Items / Commentary
DAY 0 (PREP) — Wed 9/30 — Schedule sent to Phil, meetings booked, cutoff communicated. Nothing posts yet.
1 | Day 0 (prep) | Wed 9/30 | Send final close schedule to Phil | Close mgmt | • Send this workbook (or a PDF of the Close Checklist and By Person tabs) to Phil by end of day Wednesday 9/30. • Confirm each owner has seen their rows and agrees to the dates. • Evidence: email sent, owners acknowledged. | Email | Jonathan (close lead) | N/A | N/A
2 | Day 0 (prep) | Wed 9/30 | Book the review meetings | Close mgmt | • Confirm the preliminary review with Phil on Thu 10/8 (Day 6) and the final walk-through on Mon 10/12 (Day 8) are on every owner's calendar. • Schedule the review with Nick for Wed 10/14 and include Phil. • Block Mon 10/12 afternoon and Tue 10/13 morning for presentation prep with Phil. • Evidence: calendar invites accepted. | Calendar | Jonathan (close lead) | N/A | N/A
3 | Day 0 (prep) | Wed 9/30 | Communicate September cutoff | Close mgmt | • Remind Purchasing that all PO receipts through 9/30 must be entered by Day 1 (BAU: 1 day after physical receipt). • Remind the Office Manager that all vendor invoices on hand go into INNERGY by Day 2. • Ask Project Managers for any September change orders or billings not yet submitted. • Evidence: cutoff reminders sent. | Email | Jonathan (close lead) | N/A | N/A
DAY 1 — Thu 10/1 — Cash in the door. Everything that touched the bank is recorded.
4 | Day 1 | Thu 10/1 | Cash Receipts Entered | AR | • Post every customer payment received through 9/30 (checks, ACH, wires, card, lockbox) for both entities. • Apply each receipt to the open invoice or record it as a customer deposit; leave nothing unapplied without a note. • Tie total receipts posted for September to the bank deposit detail. • Evidence: receipts posted, unapplied cash list reviewed. | NetSuite, bank portal | AR
5 | Day 1 | Thu 10/1 | Bank and Credit Card Activity Entered | GL | • Bring in all bank and credit card transactions dated through 9/30 for every account in both entities. • Code each item to the right GL account and job; clear the uncategorized or suspense list to zero. • Match transactions in NetSuite to the bank so nothing is duplicated or missed. • Evidence: no unmatched or uncoded items dated in September. | NetSuite, bank and card portals | Transaction Specialist
6 | Day 1 | Thu 10/1 | Vendor Prepayments Entered | AP | • Record every deposit or down payment sent to a vendor in September (import POs, installer contracts, equipment). • Reference the PO or contract on each prepayment so it can be applied on Day 2. • Confirm each prepayment cleared the bank in September. • Evidence: prepayment list with PO reference for every item. | NetSuite, INNERGY POs | Transaction Specialist
7 | Day 1 | Thu 10/1 | Payroll Entered | Labor | • Post every payroll run with a September pay date from the payroll provider register, for both entities. • Record gross wages, employer taxes, benefits, and deductions to the right accounts and departments. • Allocate shop and install labor to jobs where the company tracks it. • Evidence: payroll journal ties to the provider's register and to the cash paid. | Payroll provider, NetSuite | Sr. Accountant
8 | Day 1 | Thu 10/1 | Send End-of-Day Tracker to Phil | Close mgmt | • Update this checklist with Y/N for each entity and send it to Phil at the end of the day. • If behind schedule, include a plan to get back on schedule (what, who, by when). • Evidence: tracker email sent. | Email | Jonathan (close lead) | N/A | N/A
DAY 2 — Fri 10/2 — Billing and vendor cutoff. All invoices, payments, and payroll for September are in the system.
9 | Day 2 | Fri 10/2 | AR Invoices Entered | AR | • Enter all progress billings, pay applications, change orders, and final billings for work through 9/30, dated in September. • Confirm every job with billable activity in INNERGY has an invoice or a written reason it was not billed. • Record retainage and sales tax correctly on each invoice. • Evidence: September billing log agrees to invoices posted. | NetSuite, INNERGY | Transaction Specialist
10 | Day 2 | Fri 10/2 | AP Invoices Entered | AP | • Enter every vendor invoice on hand in INNERGY (Office Manager) and NetSuite (Transaction Specialist), dated in the month the goods or services were received. • Match each invoice to its PO and receipt; log disputed invoices with the reason. • List invoices expected but not yet received so they can be accrued on Day 3. • Evidence: AP entry log, disputed invoice list, expected-but-not-received list. | INNERGY, NetSuite | Transaction Specialist (Office Manager for INNERGY)
11 | Day 2 | Fri 10/2 | AP Payments Entered | AP | • Record every check, ACH, and card payment to vendors dated through 9/30 and apply it to the bill it paid. • Void or reissue stale and returned payments. • Confirm lien waivers were requested for sub and supplier payments that need one. • Evidence: payment register ties to the bank; no unapplied payments. | NetSuite, bank portal | Transaction Specialist
12 | Day 2 | Fri 10/2 | Vendor Prepayments Applied | AP | • Apply each prepayment to the vendor bill it was paid against once the bill is entered (same day as AP invoices). • Support every remaining prepayment balance with an open PO or contract. • Flag prepayments older than the expected delivery date for follow-up with Purchasing. • Evidence: prepayment balance list agrees to the GL. | NetSuite, INNERGY POs | Transaction Specialist
13 | Day 2 | Fri 10/2 | Payroll Accrual Entered | Labor | • Accrue wages earned from the last September pay period end through 9/30, plus employer taxes and benefits on those wages. • Use hours from timekeeping and current pay rates; note the method on the entry. • Post a reversing entry dated 10/1. • Evidence: accrual workpaper showing days accrued and rates used. | Timekeeping, payroll provider, NetSuite | Sr. Accountant
14 | Day 2 | Fri 10/2 | Send End-of-Day Tracker to Phil | Close mgmt | • Update this checklist with Y/N for each entity and send it to Phil at the end of the day. • If behind schedule, include a plan to get back on schedule (what, who, by when). • Evidence: tracker email sent. | Email | Jonathan (close lead) | N/A | N/A
WEEKEND — Sat 10/3 – Sun 10/4 — No scheduled work. Catch-up only if Day 1 or Day 2 items are behind.
DAY 3 — Mon 10/5 — Revenue decided, AR and AP closed, accruals and schedules done.
15 | Day 3 | Mon 10/5 | Revenue Recognition Complete | AR | • Review each active job's status, percent complete, and billings to date against the contract. • Compute over-billings and under-billings and post the entries per company policy. • Confirm customer deposits are still deferred and not recognized as revenue. • Evidence: revenue schedule by job, signed off. | INNERGY, NetSuite | CFO
16 | Day 3 | Mon 10/5 | Accounts Receivable Closed | AR | • Run the AR aging as of 9/30 and resolve unapplied cash, credits, and small balances. • Review past-due accounts and note collection actions. • Confirm the AR aging total agrees to the AR general ledger balance for each entity. • Evidence: aging saved with the close, subledger-to-GL tie-out noted. | NetSuite | Transaction Specialist
17 | Day 3 | Mon 10/5 | Accounts Payable Closed | AP | • Run the AP aging as of 9/30 and confirm it agrees to the AP general ledger balance for each entity. • Resolve debit balances, duplicate bills, and unapplied vendor credits. • Confirm no bills dated in September remain unposted or in approval. • Evidence: aging saved with the close, subledger-to-GL tie-out noted. | NetSuite | Transaction Specialist
18 | Day 3 | Mon 10/5 | Accrued Receipts | GL | • Run the received-not-invoiced report for PO receipts through 9/30 and accrue the cost to the job or inventory. • Accrue known services received but not yet billed (subs, freight, utilities, professional fees) from the Day 2 list. • Post reversing entries dated 10/1. • Evidence: accrual workpaper with report and supporting emails or POs. | INNERGY, NetSuite | Sr. Accountant
19 | Day 3 | Mon 10/5 | Prepaids Reconciled | GL | • Add new prepaid items (insurance, software, rent, licenses) to the prepaid schedule with start and end dates. • Post September amortization for every item on the schedule. • Confirm the schedule total agrees to the prepaid GL balance. • Evidence: updated prepaid schedule saved with the close. | NetSuite | Sr. Accountant
20 | Day 3 | Mon 10/5 | Customer Deposits Reconciled | GL | • List customer deposits on hand by customer and job. • Add deposits received in September and relieve deposits applied to invoices. • Confirm the list agrees to the customer deposit GL balance and to the job list. • Evidence: deposit schedule by job. | NetSuite, INNERGY | Sr. Accountant
21 | Day 3 | Mon 10/5 | Send End-of-Day Tracker to Phil | Close mgmt | • Update this checklist with Y/N for each entity and send it to Phil at the end of the day. • If behind schedule, include a plan to get back on schedule (what, who, by when). • Evidence: tracker email sent. | Email | Jonathan (close lead) | N/A | N/A
DAY 4 — Tue 10/6 — Reconcile every balance sheet account. Inventory, COGS, and WIP land in September.
22 | Day 4 | Tue 10/6 | Balance Sheet Accounts Reconciled | GL | • Reconcile every bank and credit card account to the 9/30 statement; clear reconciling items. • Reconcile fixed assets and post depreciation; reconcile loans and post interest. • Reconcile accrued liabilities, sales tax payable, payroll liabilities, intercompany (Foundation vs. Cambria), and any other account with activity. • Evidence: a reconciliation with support for every balance sheet account, signed and dated. | NetSuite, bank and lender statements | Sr. Accountant
23 | Day 4 | Tue 10/6 | Inventory Reconciliation Completed | Inventory | • Pull the INNERGY inventory valuation as of 9/30 and compare it to the inventory GL balance. • Post cycle count adjustments and explain every variance above the threshold. • Review slow-moving and obsolete items with Purchasing. • Evidence: inventory rec with variance explanations. | INNERGY, NetSuite | Sr. Accountant
24 | Day 4 | Tue 10/6 | Material COGS Journal Entry Entered | Inventory | • Pull material consumed on jobs in September from INNERGY. • Relieve inventory and charge material cost of goods sold by job. • Confirm the entry agrees to the consumption report and the inventory rec. • Evidence: consumption report attached to the journal entry. | INNERGY, NetSuite | Sr. Accountant
25 | Day 4 | Tue 10/6 | WIP Journal Entry Entered | Inventory | • Identify jobs in production at 9/30 that have not shipped or been billed. • Move material and labor cost on those jobs into work in process; roll forward August WIP. • Confirm the WIP schedule agrees to the WIP GL balance. • Evidence: WIP schedule by job. | INNERGY, NetSuite | Sr. Accountant
26 | Day 4 | Tue 10/6 | Send End-of-Day Tracker to Phil | Close mgmt | • Update this checklist with Y/N for each entity and send it to Phil at the end of the day. • If behind schedule, include a plan to get back on schedule (what, who, by when). • Evidence: tracker email sent. | Email | Jonathan (close lead) | N/A | N/A
DAY 5 — Wed 10/7 — Job accruals, draft statements for both entities and consolidated, open item list written.
27 | Day 5 | Wed 10/7 | Unbilled Labor Accrual Entered | Labor | • Identify install and shop labor performed on jobs through 9/30 that has not yet been billed to the customer. • Accrue the related revenue and cost consistent with the Day 3 revenue recognition. • Post a reversing entry dated 10/1. • Evidence: unbilled labor workpaper by job. | INNERGY, timekeeping, NetSuite | CFO
28 | Day 5 | Wed 10/7 | Unfulfilled Material Accrual Entered | Inventory | • Identify material billed or committed to customers but not yet delivered or installed at 9/30. • Accrue the cost so it lands in the same month as the revenue. • Post a reversing entry dated 10/1. • Evidence: unfulfilled material workpaper by job. | INNERGY, NetSuite | CFO
29 | Day 5 | Wed 10/7 | Income Statement Accounts Reviewed (flux) | GL | • Compare each revenue and expense account to August, September budget, and prior year; flag changes above the review threshold. • Scan detail for miscoded items, personal or non-business charges, and items posted to the wrong job. • Check that job cost by category (material, labor, sub, other) looks reasonable against production activity. • Evidence: flux review with every flagged line carried to the open item list. | NetSuite | Sr. Accountant
30 | Day 5 | Wed 10/7 | Draft Financial Statements — Foundation and Cambria | Financial | • Prepare the draft income statement, balance sheet, and cash flow for September and year to date for each entity. • Confirm each statement ties to the trial balance and to the reconciliations from Day 4. • Evidence: draft statements saved with the close. | NetSuite | Sr. Accountant
31 | Day 5 | Wed 10/7 | Draft Consolidated Financial Statements | Financial | • Combine Foundation and Cambria; identify and eliminate intercompany balances and transactions. • Phil assists with the consolidation format; scope is limited for this close. • Evidence: consolidated draft with an elimination schedule. | NetSuite, consolidation workbook | Sr. Accountant + Phil (fractional CFO)
32 | Day 5 | Wed 10/7 | Open Item List Written | Financial | • Write down every question, unexplained variance, and suspected error from the flux review and draft statements. • Assign an owner and a target answer date (Day 6) to each item. • Evidence: open item list sent with the Day 5 end-of-day tracker. | Tracker | Jonathan (close lead) + Sr. Accountant
33 | Day 5 | Wed 10/7 | Send End-of-Day Tracker to Phil | Close mgmt | • Update this checklist with Y/N for each entity and send it to Phil at the end of the day. • If behind schedule, include a plan to get back on schedule (what, who, by when). • Evidence: tracker email sent. | Email | Jonathan (close lead) | N/A | N/A
DAY 6 — RESEARCH — Thu 10/8 — Research day. Preliminary review with Phil. Run down every open item; draft the commentary. No adjustments posted yet.
34 | Day 6 | Thu 10/8 | Research Open Items and Variances | Financial | • Work every item on the open item list: pull invoices, POs, job records, bank detail, and payroll registers. • Talk to Purchasing, Production, and Project Managers where the answer is outside accounting. • Document what was found and the proposed fix (or no change needed) for each item. No adjustments post today. • Evidence: open item list updated with findings and proposed adjustments. | NetSuite, INNERGY, source documents | Each item's owner
35 | Day 6 | Thu 10/8 | Preliminary Review with Phil | Meeting | • Walk Phil through the draft statements for both entities and consolidated. • Most items complete; the team presents what it is digging into and the commentary drafted so far. • Capture Phil's questions as new open items with owners. • Evidence: meeting notes added to the open item list. | Meeting | Jonathan (close lead), Sr. Accountant, CFO, Phil (fractional CFO) | N/A | N/A
36 | Day 6 | Thu 10/8 | Draft Commentary for Every Variance | Financial | • For each flagged line, write the plain-language explanation (what changed, why, one-time or ongoing). • Commentary is the input to the presentation; write it so Nick can read it without a walkthrough. • Evidence: commentary column filled on the open item list. | Tracker | Each item's owner
37 | Day 6 | Thu 10/8 | Send End-of-Day Tracker to Phil | Close mgmt | • Update this checklist with Y/N for each entity and send it to Phil at the end of the day. • If behind schedule, include a plan to get back on schedule (what, who, by when). • Evidence: tracker email sent. | Email | Jonathan (close lead) | N/A | N/A
DAY 7 — ADJUST — Fri 10/9 — Adjustment day. Post approved fixes, re-run statements, finish commentary, lock both entities.
38 | Day 7 | Fri 10/9 | Adjustments Posted | Financial | • Post the adjusting entries approved by the CFO from the research day, with support attached, in the right entity. • Re-run any reconciliation an adjustment touched. • Evidence: adjustment log listing every entry, amount, and approver. | NetSuite | Sr. Accountant
39 | Day 7 | Fri 10/9 | Statements Re-Run and Re-Reviewed | Financial | • Re-run Foundation, Cambria, and consolidated statements after adjustments. • Confirm each open item is now closed or carried forward with a written reason. • Evidence: final statements, closed open item list. | NetSuite, consolidation workbook | Sr. Accountant + CFO
40 | Day 7 | Fri 10/9 | Commentary and Notes Finalized | Financial | • Finalize commentary for every variance so nothing is left to explain on Day 8. • Evidence: commentary complete and reviewed by Jonathan. | Tracker | Jonathan (close lead)
41 | Day 7 | Fri 10/9 | Accounting Periods Locked — Both Entities | Financial | • Lock September in NetSuite for Foundation and Cambria once the CFO signs off. • Evidence: period locked, sign-off noted in the tracker. | NetSuite | Sr. Accountant (after CFO sign-off)
42 | Day 7 | Fri 10/9 | Send End-of-Day Tracker to Phil | Close mgmt | • Update this checklist with Y/N for each entity and send it to Phil at the end of the day. • If behind schedule, include a plan to get back on schedule (what, who, by when). • Evidence: tracker email sent. | Email | Jonathan (close lead) | N/A | N/A
WEEKEND — Sat 10/10 – Sun 10/11 — No scheduled work. Everything should already be final.
DAY 8 — FINAL — Mon 10/12 — Walk-through with Phil, 100% final. Actuals into budget, metrics, then presentation prep begins.
43 | Day 8 | Mon 10/12 | Final Walk-Through with Phil | Meeting | • Present the final statements, reconciliations, and commentary. Everything is 100% final. • Evidence: Phil sign-off recorded in the tracker. | Meeting | Jonathan (close lead), Sr. Accountant, CFO, Phil (fractional CFO) | N/A | N/A
44 | Day 8 | Mon 10/12 | Monthly Actuals Entered in Budget | Financial | • Enter final September actuals into the budget file by account and department for each entity. • Refresh the budget-to-actual variance for the month and year to date. • Evidence: budget file updated and saved for September. | Budget file, NetSuite | Sr. Accountant + CFO
45 | Day 8 | Mon 10/12 | Metrics Prepared for Month | Financial | • Update the monthly metrics package (margin by job, backlog, cash, AR and AP aging, labor efficiency, and any others tracked). • Confirm every metric ties to the final statements. • Evidence: metrics package saved with the close. | Final statements, INNERGY | CFO
46 | Day 8 | Mon 10/12 | Presentation Prep Begins | Presentation | • Remainder of Monday: build the presentation with Phil from the final statements, metrics, and finished commentary. • Evidence: presentation draft. | Presentation | Jonathan (close lead) + Phil (fractional CFO) | N/A | N/A
47 | Day 8 | Mon 10/12 | Send End-of-Day Tracker to Phil | Close mgmt | • Update this checklist with Y/N for each entity and send it to Phil at the end of the day. • If behind schedule, include a plan to get back on schedule (what, who, by when). • Evidence: tracker email sent. | Email | Jonathan (close lead) | N/A | N/A
POST-CLOSE — Tue 10/13 – Wed 10/14 — Presentation finished and sent to Nick 24 hours ahead; review with Nick Wednesday 10/14.
48 | Post-close | Tue 10/13 | Presentation Finished and Sent to Nick (Tue 10/13) | Presentation | • Finish the presentation Tuesday morning with Phil. • Send to Nick no later than 24 hours before the Wednesday review. • Evidence: email to Nick, Phil copied. | Email | Jonathan (close lead) + Phil (fractional CFO) | N/A | N/A
49 | Post-close | Wed 10/14 | Review with Nick (Wed 10/14) | Presentation | • Review meeting with Nick, Phil included. • Capture follow-ups for the October close. • Evidence: meeting held, follow-up list. | Meeting | Jonathan (close lead) + Phil (fractional CFO) | N/A | N/A
Example of a completed row (for format only):
4 | Day 1 | Thu 10/1 | Cash Receipts Entered | AR | (see step 4) | NetSuite, bank portal | AR | Y | Y | JS 10/1/2026 | Two unapplied receipts ($1,240 total) parked in customer deposits pending customer confirmation. Follow up Day 3.
Yellow = research and adjustment steps. Green = meetings and deliverables to Phil or Nick. Columns I through L are typed by hand. No formulas or automation in this file.

## Read Me
FMS — September 2026 Close: How to Use This Workbook
Topic | Guidance
Purpose | One tracker for the September close for Foundation and Cambria: all closing tasks, by person, by day, on an 8-day close ending Monday 10/12. Nothing in this workbook is automated: every cell is typed by hand, and there are no formulas, macros, or links to NetSuite or INNERGY.
Where it came from | Built from the existing FMS Department Checklist and Phil Hammond's 9/30 email setting the September close schedule. The original 25 activities are all here, re-sequenced into the 8 days.
The 8 days | Day 1 Thu 10/1, Day 2 Fri 10/2, weekend, Day 3 Mon 10/5, Day 4 Tue 10/6, Day 5 Wed 10/7, Day 6 Thu 10/8 (research, preliminary review with Phil), Day 7 Fri 10/9 (adjustments), weekend, Day 8 Mon 10/12 (final walk-through). Post-close: send to Nick Tue 10/13, review with Nick Wed 10/14.
Research and adjustment days | Two days are reserved for research and adjustment. Day 6 is research only: run down every open item and draft the commentary, post nothing. Day 7 is adjustment: post approved fixes, re-run statements, finish commentary, lock both entities. Those rows are shaded yellow.
Two entities | Each step has a Foundation column and a Cambria column. Type Y when the step is done for that entity, N/A if it does not apply, and leave blank while open. A step is complete only when both columns are Y or N/A.
Daily tracker | The last row of every close day is the end-of-day tracker email to Phil. If any step for that day is not Y, the email includes a recovery plan: what is open, who owns it, and when it will be done.
Marking complete | Put initials and date in Completed By / Date. Anything unresolved, plus the explanation for any variance, goes in Notes / Open Items / Commentary. That column becomes the source for the presentation to Nick.
Detail column | What Done Looks Like lists the sub-steps and the evidence that should exist before a step is marked Y. Treat it as the minimum and add to it as the team learns what tends to go wrong.
Tabs | Close Checklist: the full list by day. By Person: the same steps laid out per owner per day, for the daily stand-up. Close Calendar: one line per day. The two BAU tabs are carried over from the original file with only typo fixes; they set the daily cadence that makes an 8-day close possible.
Owners | Owners are the roles from the original checklist (AR, Transaction Specialist, Sr. Accountant, CFO, Office Manager), plus Jonathan as close lead and Phil as fractional CFO. Rows assigned to CFO in the original are kept as CFO; reassign if Phil intends those to sit with Jonathan.
Colors | Blue banner = a close day. Yellow = research and adjustment steps, and cells to type in. Green = meetings and deliverables to Phil or Nick.

## By Person
FMS — September 2026 Close: Steps by Person by Day
Responsible Party | Day 0 (prep) Wed 9/30 | Day 1 Thu 10/1 | Day 2 Fri 10/2 | Day 3 Mon 10/5 | Day 4 Tue 10/6 | Day 5 Wed 10/7 | Day 6 — RESEARCH Thu 10/8 | Day 7 — ADJUST Fri 10/9 | Day 8 — FINAL Mon 10/12 | Post-close Tue 10/13 – Wed 10/14
AR |  | 4. Cash Receipts Entered |  |  |  |  | 34. Research Open Items and Variances (shared) 36. Draft Commentary for Every Variance (shared)
Transaction Specialist |  | 5. Bank and Credit Card Activity Entered 6. Vendor Prepayments Entered | 9. AR Invoices Entered 10. AP Invoices Entered (shared) 11. AP Payments Entered 12. Vendor Prepayments Applied | 16. Accounts Receivable Closed 17. Accounts Payable Closed |  |  | 34. Research Open Items and Variances (shared) 36. Draft Commentary for Every Variance (shared)
Office Manager |  |  | 10. AP Invoices Entered (shared)
Sr. Accountant |  | 7. Payroll Entered | 13. Payroll Accrual Entered | 18. Accrued Receipts 19. Prepaids Reconciled 20. Customer Deposits Reconciled | 22. Balance Sheet Accounts Reconciled 23. Inventory Reconciliation Completed 24. Material COGS Journal Entry Entered 25. WIP Journal Entry Entered | 29. Income Statement Accounts Reviewed (flux) 30. Draft Financial Statements — Foundation and Cambria 31. Draft Consolidated Financial Statements (shared) 32. Open Item List Written (shared) | 34. Research Open Items and Variances (shared) 35. Preliminary Review with Phil (shared) 36. Draft Commentary for Every Variance (shared) | 38. Adjustments Posted 39. Statements Re-Run and Re-Reviewed (shared) 41. Accounting Periods Locked — Both Entities (shared) | 43. Final Walk-Through with Phil (shared) 44. Monthly Actuals Entered in Budget (shared)
CFO |  |  |  | 15. Revenue Recognition Complete |  | 27. Unbilled Labor Accrual Entered 28. Unfulfilled Material Accrual Entered 31. Draft Consolidated Financial Statements (shared) | 34. Research Open Items and Variances (shared) 35. Preliminary Review with Phil (shared) 36. Draft Commentary for Every Variance (shared) | 39. Statements Re-Run and Re-Reviewed (shared) 41. Accounting Periods Locked — Both Entities (shared) | 43. Final Walk-Through with Phil (shared) 44. Monthly Actuals Entered in Budget (shared) 45. Metrics Prepared for Month 46. Presentation Prep Begins (shared) | 48. Presentation Finished and Sent to Nick (Tue 10/13) (shared) 49. Review with Nick (Wed 10/14) (shared)
Jonathan (close lead) | 1. Send final close schedule to Phil 2. Book the review meetings 3. Communicate September cutoff | 8. Send End-of-Day Tracker to Phil | 14. Send End-of-Day Tracker to Phil | 21. Send End-of-Day Tracker to Phil | 26. Send End-of-Day Tracker to Phil | 32. Open Item List Written (shared) 33. Send End-of-Day Tracker to Phil | 34. Research Open Items and Variances (shared) 35. Preliminary Review with Phil (shared) 36. Draft Commentary for Every Variance (shared) 37. Send End-of-Day Tracker to Phil | 40. Commentary and Notes Finalized 42. Send End-of-Day Tracker to Phil | 43. Final Walk-Through with Phil (shared) 46. Presentation Prep Begins (shared) 47. Send End-of-Day Tracker to Phil | 48. Presentation Finished and Sent to Nick (Tue 10/13) (shared) 49. Review with Nick (Wed 10/14) (shared)
Phil (fractional CFO) | [5 empty] | 31. Draft Consolidated Financial Statements (shared) | 35. Preliminary Review with Phil (shared) |  | 43. Final Walk-Through with Phil (shared) 46. Presentation Prep Begins (shared) | 48. Presentation Finished and Sent to Nick (Tue 10/13) (shared) 49. Review with Nick (Wed 10/14) (shared)
(shared) = more than one owner; the full owner list is on the Close Checklist tab. Step numbers match the Close Checklist tab.

## Close Calendar
FMS — September 2026 Close Calendar (day-by-day view)
Day | Date | Focus of the Day | Steps Due | Who
Day 0 (prep) | Wed 9/30 | Schedule sent to Phil, meetings booked, cutoff communicated. Nothing posts yet. | 1. Send final close schedule to Phil 2. Book the review meetings 3. Communicate September cutoff | Jonathan (close lead)
Day 1 | Thu 10/1 | Cash in the door. Everything that touched the bank is recorded. | 4. Cash Receipts Entered 5. Bank and Credit Card Activity Entered 6. Vendor Prepayments Entered 7. Payroll Entered 8. Send End-of-Day Tracker to Phil | AR Jonathan (close lead) Sr. Accountant Transaction Specialist
Day 2 | Fri 10/2 | Billing and vendor cutoff. All invoices, payments, and payroll for September are in the system. | 9. AR Invoices Entered 10. AP Invoices Entered 11. AP Payments Entered 12. Vendor Prepayments Applied 13. Payroll Accrual Entered 14. Send End-of-Day Tracker to Phil | Jonathan (close lead) Sr. Accountant Transaction Specialist Transaction Specialist (Office Manager for INNERGY)
Weekend | Sat 10/3 – Sun 10/4 | No scheduled work. Catch-up only if Day 1 or Day 2 items are behind.
Day 3 | Mon 10/5 | Revenue decided, AR and AP closed, accruals and schedules done. | 15. Revenue Recognition Complete 16. Accounts Receivable Closed 17. Accounts Payable Closed 18. Accrued Receipts 19. Prepaids Reconciled 20. Customer Deposits Reconciled 21. Send End-of-Day Tracker to Phil | CFO Jonathan (close lead) Sr. Accountant Transaction Specialist
Day 4 | Tue 10/6 | Reconcile every balance sheet account. Inventory, COGS, and WIP land in September. | 22. Balance Sheet Accounts Reconciled 23. Inventory Reconciliation Completed 24. Material COGS Journal Entry Entered 25. WIP Journal Entry Entered 26. Send End-of-Day Tracker to Phil | Jonathan (close lead) Sr. Accountant
Day 5 | Wed 10/7 | Job accruals, draft statements for both entities and consolidated, open item list written. | 27. Unbilled Labor Accrual Entered 28. Unfulfilled Material Accrual Entered 29. Income Statement Accounts Reviewed (flux) 30. Draft Financial Statements — Foundation and Cambria 31. Draft Consolidated Financial Statements 32. Open Item List Written 33. Send End-of-Day Tracker to Phil | CFO Jonathan (close lead) Jonathan (close lead) + Sr. Accountant Sr. Accountant Sr. Accountant + Phil (fractional CFO)
Day 6 — RESEARCH | Thu 10/8 | Research day. Preliminary review with Phil. Run down every open item; draft the commentary. No adjustments posted yet. | 34. Research Open Items and Variances 35. Preliminary Review with Phil 36. Draft Commentary for Every Variance 37. Send End-of-Day Tracker to Phil | Each item's owner Jonathan (close lead) Jonathan (close lead), Sr. Accountant, CFO, Phil (fractional CFO)
Day 7 — ADJUST | Fri 10/9 | Adjustment day. Post approved fixes, re-run statements, finish commentary, lock both entities. | 38. Adjustments Posted 39. Statements Re-Run and Re-Reviewed 40. Commentary and Notes Finalized 41. Accounting Periods Locked — Both Entities 42. Send End-of-Day Tracker to Phil | Jonathan (close lead) Sr. Accountant Sr. Accountant (after CFO sign-off) Sr. Accountant + CFO
Weekend | Sat 10/10 – Sun 10/11 | No scheduled work. Everything should already be final.
Day 8 — FINAL | Mon 10/12 | Walk-through with Phil, 100% final. Actuals into budget, metrics, then presentation prep begins. | 43. Final Walk-Through with Phil 44. Monthly Actuals Entered in Budget 45. Metrics Prepared for Month 46. Presentation Prep Begins 47. Send End-of-Day Tracker to Phil | CFO Jonathan (close lead) Jonathan (close lead) + Phil (fractional CFO) Jonathan (close lead), Sr. Accountant, CFO, Phil (fractional CFO) Sr. Accountant + CFO
Post-close | Tue 10/13 – Wed 10/14 | Presentation finished and sent to Nick 24 hours ahead; review with Nick Wednesday 10/14. | 48. Presentation Finished and Sent to Nick (Tue 10/13) 49. Review with Nick (Wed 10/14) | Jonathan (close lead) + Phil (fractional CFO)

## BAU Expectations - Accounting
FMS — Accounting BAU Expectations
Activity | Category | (Business) Days to Complete | Responsible Party | Complete?
Outgoing Customer Payments Recorded | AP | Next Day | Transaction Specialist
Cash Receipts Recorded | AR | Second Day | Transaction Specialist
AR Invoices Entered | AR | Third Day | Transaction Specialist
AP Invoices Entered (INNERGY) | AP | Second Day | Office Manager
AP Invoices Entered (NetSuite) | AP | Third Day | Transaction Specialist
Apply Vendor Prepayments | AP | Fourth Day | Transaction Specialist

## BAU Expectations - Purchasing
FMS — Purchasing BAU Expectations
Activity | Category | (Business) Days to Complete | Responsible Party | Complete?
PO Receipts | Purchasing | 1 after physical receipt | Purchasing Manager
PO Issued | Purchasing |  | Purchasing Manager
PO Requisition | Purchasing |  | Purchasing Manager
Installer Purchase Orders Sent | Purchasing | 1 week after contract agreement sent to purchasing | Purchasing Manager
Installer Purchase Orders Received | Purchasing | 1 after receipt of invoice | Purchasing Manager
Import Purchase Orders Created | Purchasing | 3 weeks prior to physical receipt | Purchasing Manager
Import Purchase Orders Received | Purchasing | 2 after physical receipt | Purchasing Manager